4th December 2015


Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress


Preferred Option for Flood Alleviation Scheme:
A meeting was held at the Stokeinteignhead Village Hall on November 25th where DCC presented the preferred option for a flood alleviation scheme for the village. This outlined some proposals for flood storage areas, highway improvements and an additional pipe at Victoria Farm discharging in to the watercourse. Details can be found on the presentation which has been circulated to the Parish Council, in addition to DCC’s answers to the questions raised in the smaller community meetings throughout October.
DCC are now progressing with developing the details of the scheme and the necessary surveys and further investigations alongside this.
It is hoped that works to the lower end of the village will commence in January/February 2016.

Emergency Plan:
DCC will be meeting with village and Parish representatives on 9th December to make a start on writing an Emergency Plan. Mike Rose from Contingency Planning Solutions will be assisting with this.
The rain gauge element of the plan is now moving forward. Hydrologic will be visiting the village on 8th December to finalise a location in agreement with the land owner.

Further Work and Investigations:
· Further land owner liaison and agreements are required in order to progress aspects of the scheme – currently in progress.
· Further topographical survey work is required. This is scheduled for December/January. 
· Environmental surveys are required. It is anticipated that these will start in December/January.
· Initial walk overs to determine soil types and suitability for use are to be scheduled for December. More detailed surveys will be carried out after the Christmas break.
· Trial pits and investigations in the highway are scheduled for December in the lower end of village. This will take place in February/March for other highway improvement areas.


See below: Updated Stokeinteignhead Action Plan 2015/2016 


Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Management
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	2015
	2016
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	Mar
	Apr
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	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Engineer meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Community Pathfinder Project liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Hydraulic modelling
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	Preferred option
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	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Environmental Survey
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Final PAR approval
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	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	



	 
	Not completed
	
	In progress
	
	Completed 



