5th  February 2016


Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress


Immediate works for Flood Alleviation Scheme:
Works to Victoria Farm and the adjacent highway are now substantially complete. Thank you to everyone for their patience, especially the School, Pub and Shop. We are also very grateful for the support and patience of the residents at Victoria Farm and Five Blades. We are now waiting for dryer weather in order to finish the landscaping of Victoria Farm and the headwall for the new outfall at Five Blades.
Although we were on site to address the flood risk to properties, whilst there we have also taken the opportunity to improve the highway drainage at this location, which we hope will be a noticeable improvement to the residents.
The silt trap at the Village Hall is working well to date. However, this will only continue to do so with continued maintenance and clearing out of the silt and material collected.

Further works:
[bookmark: _GoBack]Phase 1 of the geotechnical study was a desk based assessment and has now been completed. We will now be initiating procurement to appoint surveyors for Phase 2, which will involve a more detailed survey on site to determine soil type and suitability. Land owners will be engaged with throughout.
Environmental walkover surveys are now complete and we are awaiting the finished report on this.

Emergency Plan:
The Parish Council are continuing to work on an Emergency Plan for the village with the help of Mike Rose from Contingency Planning Solutions. It is intended for the plan to be exercised and put to the test sometime in March.
The rain gauge has now been installed. The Parish will be provided with further information on the calibration of this and how they can monitor the levels via a website log in. 


See below: Updated Stokeinteignhead Action Plan 2015/2016 


Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Management


Stokeinteignhead Action Plan 2015/2016
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Action
	2015
	2016

	
	Feb
	Mar
	Apr
	May
	Jun
	Jul
	Aug
	Sep
	Oct
	Nov
	Dec
	Jan
	Feb
	Mar
	Apr 
	May 
	Jun 
	Jul 
	Aug 
	Sep 

	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Engineer meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Community Pathfinder Project liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Hydraulic modelling
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Optioneering
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Costing
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Environmental Survey
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Final PAR approval
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Serve any relevant notices
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	



	 
	Not completed
	
	In progress
	
	Completed 



