3rd July 2015

Update for Stokeinteignhead Parish Council

Re: Flooding Issues and progress

This month’s update sees some positive progress. However, due to the complexity of the Stokeinteignhead catchment and the investigations required, the programme has slipped slightly into the next financial year. This detailed study has allowed for a much better understanding of the systems which will then lead to a more robust scheme, which DCC are still committed to delivering at the earliest appropriate time.

Stilt Trap at Village Hall:

Following some alterations to the silt trap design, we have now received some more suitable quotes back from contractors and so will proceed with our preferred choice. We are currently liaising with Highways to facilitate the programming of these works on the highway.

Further investigations/hydraulic modelling:

Nigel Smith is currently finalising his Catchment Study and Preliminary Flood Alleviation Options. These initial options have been discussed with the Flood Risk Management Team at DCC and we are now progressing with some further detailed survey work in order to verify the options and finalise design. Once the finished report is available it will be shared with the Parish.

Community Pathfinder Project:

DCC have started initial discussions with the village Flood Group about how the Flood Resilience Community Pathfinder Project can help. The development of an emergency plan and the use of rain gauges/flood warning systems will require more detailed discussions and investigation. Dorothee Fitzsimmons has been liaising with the Flood Group regarding this.

See below: Updated Stokeinteignhead Action Plan 2015/2016

Jessica Bott

Senior Flood Risk Officer

Devon County Council Flood Risk Management

| Stokeinteignhead Action Plan 2015/2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action | 2015 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |
|  | Jan | Feb | Mar | Apr | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb | Mar |  | Apr |
| Silt trap: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Survey and design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Procure and construct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Maintenance schedule to be agreed by Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Highway agreement/ownership notice etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Obtain LiDAR/topographic data for further work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engineer to meet with Flood Group re: village drainage plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Pathfinder Project to liaise with Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hydraulic modelling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Optioneering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Costing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production of Project Appraisal Report (PAR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental report/statement: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Outline further investigations necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outline design for PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Detailed design of preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Serve any relevant notices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Parish Council/residents comms and updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Not completed |
| --- | --- |
|  | In progress |
|  | Completed |