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Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress


We have been making positive progress this month developing various options for the first phase of a scheme for the village, which will compliment any upstream storage areas as part of a second phase.
A topographical survey has now been produced for the northern end of the village covering the areas of Stoke Road and along the existing watercourse through Victoria Farm, Five Blades and Random Cottage. However, further more detailed drainage investigations may still be required here.
We are now in discussions with our contractors South West Highways regarding trial pit locations and drainage/gully improvements in the Forches Hill and Church Lane area. A proposal has been drawn up and we are now awaiting a price. 
We are still finalising the details on options for upstream storage areas as part of any second phase works.

Stilt trap at village hall:
Recent inspection of the silt trap by DCC shows that it is working well and collecting material that would otherwise have been washed into the highway drainage system. Continuing performance however is dependent on regular maintenance and we would encourage the Parish to activate their management plan to clear the material to ensure maximum efficiency of the silt trap.
Community resilience measures and flow monitoring:
We are now progressing with the installation of a rain gauge, It has been determined through site visits that there are no suitable sites in the village for a water level or flow gauge but there is opportunity for a rain gauge. We are still trying to find a location for this and discussions are ongoing with local land owners, residents and the Flood Group to find the most suitable place with the best conditions. Once this is determined we can progress with installation and monitoring. This will then feed in to a local emergency plan for the village which we will be assisting with writing, in addition to providing a supply of flood resilience equipment and storage area for the village.
Upcoming local meetings:
An evening meeting is to be held at the village hall on 25th November where DCC Flood Risk Management will put forward the current proposals for the village and provide an opportunity to discuss these and answer questions. We will also be there to answer those questions raised during the series of smaller meetings throughout October.







Further investigations:
Section 5 of the report lists further survey and study required. Below shows our progress in working through these recommendations:
	a) Obtain copy of Teignbridge District Council infiltration study undertaken for SWW and consider against flood alleviation options; 
	Completed

	b) An inspection of the planning file for Hollifields, Lower Gabwell and the properties in Ivy Tree Hill; 
	DCC to bring to attention of Teignbridge Planning

	c) Obtain copies of utility records for Deane Road, Ivy Tree Hill and Stoke Road: BT, WPD, and WWU; 
	In progress

	d) Investigate blockage to arch culvert at Home Farm Court; 
	In progress

	e) Survey watercourse, manhole and pipe branch entering MH5504 from Church House Inn;
	DCC to schedule

	f) CCTV camera and level survey of the pipe system between Hilary Cottage and The Firs; 
	Completed + DCC Highways now clearing blockages found.

	g) Topographical survey of land adjacent to and south of Deane House identified for flood storage and cut off ditches; 
	Completed

	h) Topographical survey of Deane Road if additional gullies are to be constructed;
	Completed

	i) BRE 365 Infiltration tests at Teignharvey Lane if infiltration is to be considered;
	n/a at this stage

	j) CCTV survey of gullies and pipes in Ivy Tree Hill  Stoke Cross to determine capacity; 
	DCC yet to schedule
Topographical survey completed

	k) Open MH5521 or MH5524 to confirm depths and connectivity (Outside Victoria Farm);
	DCC to schedule
Topographical survey completed

	l) Topographical survey of land between Village Hall and Pools Weir Road identified for flood storage.  This should include SWW MH cover levels, invert levels and pipe branches even if chambers are buried; 
	
Completed

	m) Topographical survey of land between Hilary Cottage and The Mead if insufficient volume is available between the Village Hall and Pools Weir Road. 
	Option no longer to be progressed. Point n) now to be progressed in line with alternative option.

	n) Topographical survey of Stoke Road – Victoria Farm – Five Blades – Random Cottage 
	Completed




See below: Updated Stokeinteignhead Action Plan 2015/2016 


Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Managemet


Stokeinteignhead Action Plan 2015/2016
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Action
	2015
	2016

	
	Feb
	Mar
	Apr
	May
	Jun
	Jul
	Aug
	Sep
	Oct
	Nov
	Dec
	Jan
	Feb
	Mar
	Apr 
	May 
	Jun 
	Jul 
	Aug 
	Sep 

	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Engineer meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Community Pathfinder Project liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Hydraulic modelling
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Optioneering
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Costing
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Environmental Survey
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Final PAR approval
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Serve any relevant notices
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	



	 
	Not completed
	
	In progress
	
	Completed 



