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Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress


Highway improvement works started the week commencing Monday 2nd March, to improve buddle holes in locations 3 and 4 marked on the plan below. Locations 1 and 2 have not been progressed as the land owner concerned required further works and measures to avoid increased surface water and silts on the land. Any measures to consider here could be costly and so should be developed in conjunction with the main scheme.

Our consultant engineer, Nigel Smith has started work to build upon Robin Selby’s report and to develop a more detailed survey of the area on which the main scheme design can be based.

To date, Nigel has:
· Reviewed Robin’s report and the existing CCTV and channel surveys;
· Attended the site to check flow routes from gates/fields and further hydraulic analysis (partially complete);
· Completed a level and dimension survey of the green lane adjacent to Stoke Road for the proposed silt trap;
· Started to build the hydraulic model to determine the current drainage system capacity and the effect of upsizing any limiting structures;
· Nigel is yet to meet with Fred Corns of the Parish Flood Group but is likely to arrange this within the next week.
· Draft report with recommendations is yet to be completed.

Stilt Trap at Village Hall:
The proposed silt trap is now with DCC at the detailed design stage, anticipating going to contractors in March/April.
Robin Selby will be producing a management plan that the Parish can use or adapt to manage the maintenance of the silt trap once it is installed.
Funding:
The Devon Local Flood Risk Management Strategy Action Plan is to go to DCC Cabinet for approval this month. This plan includes the allocation of funding for Stokeinteignhead for the financial year April 2015 – March 2016 which will help to continue to progress the study and Main Scheme.


See below: Updated Stokeinteignhead Action Plan 2015/2016 and drainage improvement locations.



Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Management
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Plan of drainage improvement locations.




	Stokeinteignhead Action Plan 2015/2016
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Action
	2015
	2016

	
	Jan
	Feb
	Mar
	Apr
	May
	Jun
	Jul
	Aug
	Sep
	Oct
	Nov
	Dec
	Jan
	Feb
	Mar

	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Engineer to meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Community Pathfinder Project to liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Hydraulic modelling
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Optioneering
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Costing
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Serve any relevant notices
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 



	 
	Not completed

	
	In progress

	 
	Completed 
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