8th  March 2016

Stokeinteignhead Parish Council Update

Flooding Alleviation Works

Immediate works for Flood Alleviation Scheme:

Drainage improvement works in Forches Hill to install a series of new gullies and drains were completed last week. Drainage improvement works are currently taking place in Church Lane this week to also install further gullies and drains.

Further landscaping work is still required at Victoria Farm and the flap valve is still to be installed at Five Blades, just awaiting delivery of the valve to South West Highways from the manufacturer.

The silt trap at the Village Hall is working well to date. However, this will only continue to do so with continued maintenance and clearing out of the silt and material collected.

Further works:

We are still in the process of initiating procurement to appoint surveyors to carry out a detailed survey on site to determine soil type and suitability for any flood storage areas. Land owners will be engaged with throughout.

Environmental walkover surveys are now complete and we have received the finished report.

We are now in discussions with our in house design team at DCC on how best to develop the technical design of the scheme.

The attached action plan is then to be updated to show the timescale for production and submission of Project Appraisal Report (PAR) to obtain any national funding, as this has now slipped slightly.

Emergency Plan:

The Parish Council are continuing to work on an Emergency Plan for the village with the help of Mike Rose from Contingency Planning Solutions. It is intended for the plan to be exercised and put to the test in May and not March, as stated in the February briefing note.

The Parish are also in the process of using the DCC community resilience grant to purchase resilience equipment for the village and also to help support the production and testing of the emergency plan.

The rain gauge has now been installed. The Parish will be provided with further information on the calibration of this and how they can monitor the levels via a website log in. The arrangements for maintenance and training still need to be finalised by DCC with Hydro-Logic.

See below: Updated Stokeinteignhead Action Plan 2015/2016

Jessica Bott

Senior Flood Risk Officer

Devon County Council Flood Risk Management

Stokeinteignhead Action Plan 2015/2016

| Action | 2015 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Feb | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May | Jun | Jul | Aug |  | Sep |  |
| Silt trap: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Survey and design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Procure and construct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Maintenance schedule to be agreed by Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Highway agreement/ownership notice etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Obtain LiDAR/topographic data for further work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engineer meet with Flood Group re: village drainage plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Pathfinder Project liaise with Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hydraulic modelling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Optioneering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Costing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production of Project Appraisal Report (PAR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental report/statement: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Environmental Survey |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Outline further investigations necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outline design for PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Detailed design of preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final PAR approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Serve any relevant notices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Parish Council/residents comms and updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Not completed |  | In progress |  | Completed |
| --- | --- | --- | --- | --- | --- |