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Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress


Stilt Trap at Village Hall:
Prices have been received back from the contractors but unfortunately all 3 were significantly more than expected. Therefore alterations have now been made to the design to bring the costs down and have been sent out for pricing again.
Concerns with the maintenance of the silt trap and insurance measures have been raised with DCC. Therefore, some more detailed guidance will be sought for the Parish, in addition to some examples of where other Parish Councils already have similar systems in place. 

Further investigations/hydraulic modelling:
Our consultant engineer, Nigel Smith has met with Councillor Chris Clarance and walked the site, in addition to obtaining detailed local flood records to be incorporated into the report.
Nigel is hoping to finish the report within the next 10 days with preliminary flood alleviation scheme options to investigate further.

Community Pathfinder Project:
DCC have started initial discussions with the village Flood Group about how the Flood Resilience Community Pathfinder Project can help. The development of an emergency plan and the use of rain gauges/flood warning systems will require more detailed discussions and investigation. Dorothee Fitzsimmons will be liaising with the Flood Group regarding this.  


See below: Updated Stokeinteignhead Action Plan 2015/2016 


Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Management
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	Action
	2015
	2016

	
	Jan
	Feb
	Mar
	Apr
	May
	Jun
	Jul
	Aug
	Sep
	Oct
	Nov
	Dec
	Jan
	Feb
	Mar

	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Engineer to meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Community Pathfinder Project to liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Hydraulic modelling
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Optioneering
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Costing
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Serve any relevant notices
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 



	 
	Not completed

	
	In progress

	 
	Completed 



