5th June 2015

Update for Stokeinteignhead Parish Council

Re: Flooding Issues and progress

Stilt Trap at Village Hall:

Prices have been received back from the contractors but unfortunately all 3 were significantly more than expected. Therefore alterations have now been made to the design to bring the costs down and have been sent out for pricing again.

Concerns with the maintenance of the silt trap and insurance measures have been raised with DCC. Therefore, some more detailed guidance will be sought for the Parish, in addition to some examples of where other Parish Councils already have similar systems in place.

Further investigations/hydraulic modelling:

Our consultant engineer, Nigel Smith has met with Councillor Chris Clarance and walked the site, in addition to obtaining detailed local flood records to be incorporated into the report.

Nigel is hoping to finish the report within the next 10 days with preliminary flood alleviation scheme options to investigate further.

Community Pathfinder Project:

DCC have started initial discussions with the village Flood Group about how the Flood Resilience Community Pathfinder Project can help. The development of an emergency plan and the use of rain gauges/flood warning systems will require more detailed discussions and investigation. Dorothee Fitzsimmons will be liaising with the Flood Group regarding this.

See below: Updated Stokeinteignhead Action Plan 2015/2016

Jessica Bott

Senior Flood Risk Officer

Devon County Council Flood Risk Management

| Stokeinteignhead Action Plan 2015/2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action | 2015 |  |  |  |  |  |  |  |  |  |  |  | 2016 |  |  |
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| Silt trap: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Survey and design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Procure and construct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Maintenance schedule to be agreed by Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Highway agreement/ownership notice etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Obtain LiDAR/topographic data for further work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Engineer to meet with Flood Group re: village drainage plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Community Pathfinder Project to liaise with Parish |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hydraulic modelling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Optioneering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Costing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Production of Project Appraisal Report (PAR) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental report/statement: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Outline further investigations necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outline design for PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submit PAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Detailed design of preferred option |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Serve any relevant notices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tender review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construction phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Parish Council/residents comms and updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Not completed |
| --- | --- |
|  | In progress |
|  | Completed |