9th October 2015


Update for Stokeinteignhead Parish Council
Re: Flooding Issues and progress

[bookmark: _GoBack]Councillor Chris Clarance and Councillor Stuart Hughes met with members of the Flood Risk Management Team on Friday 9th Oct for an update on the recent report, its outcomes and the next steps:
Further refinements are being made to the hydrology figures used in the report to re-assess the storage requirements proposed upstream. These figures are now indicating that the catchment would in fact generate smaller flows and therefore smaller storage areas would be required to protect the village. This upstream storage would be in conjunction with other recommended improvements from the report. These include improvements to the highway drainage system which would allow surface water flows into the large box culvert which runs through the village. The box culvert is currently not being utilised in times of flood as the flows cannot get into it. These works would remove water off of the road and allow it into the system, avoiding flows travelling through the village and the large ponding in the road by Victoria Farm.
To progress with these highway drainage improvements, we still need to obtain detailed information on sections of the drainage in several locations. We will be commissioning a series camera surveys to do this. We are also awaiting new proposals for the storage areas using the refined hydrology figures. We will then be looking at options of delivering the improvements in separate phases in order to enable us to deliver the whole scheme as quickly as possible.
Nigel Smith has also completed three summary documents which simplify the report for the three main areas of the village:
· Dean Road – Stoke Cross;
· Forches Hill, Ivy Tree Hill & Church Lane to Stoke Cross and;
· Higher Gabwell – Village Hall. 
These documents are attached with this update.
Stilt trap at village hall:
Works to install the silt trap are now complete. Maintenance of this will be overseen by the Parish Council. Public Rights of Way are aware of the silt trap and its maintenance and insurance requirements. Further discussions with Parish are now required to finalise maintenance management plan.
Community resilience measures and flow monitoring:
We are now progressing with the installation of a rain gauge in the village in addition to possible river level and flow gauges. Discussions are ongoing with local land owners, residents and the Flood Group to find the most suitable place to site the rain gauge. Once this is determined we can progress with installation and monitoring. This will then feed in to a local emergency plan for the village which we will be assisting with writing, in addition to providing a supply of flood resilience equipment and storage area for the village.
Upcoming local meetings:
The local Flood Group are setting up a series of meetings to discuss and answer questions on the three main areas of the village where flooding issues occur. The preliminary meetings dates are set out below. There will then be a larger open meeting to be scheduled in November. Representatives from the Flood Risk Management Team will attend in addition to our consultant Nigel Smith. 

· Dean Road and Centre: Meeting to be held 19th Oct.
Local contact Fred Corns
· Forches Hill and Ivy Tree Lane: Meeting to be held on 28th Oct.
Local contact Clive Smith.
· Lower Gabwell: Meeting date yet to be confirmed.
Local contact Bernard Stanley

Further investigations:
Section 5 of the report lists further survey and study required. Below shows our progress in working through these recommendations:
	a) Obtain copy of Teignbridge District Council infiltration study undertaken for SWW and consider against flood alleviation options; 
	Completed

	b) An inspection of the planning file for Hollifields, Lower Gabwell and the properties in Ivy Tree Hill; 
	DCC to bring to attention of Teignbridge Planning

	c) Obtain copies of utility records for Deane Road, Ivy Tree Hill and Stoke Road: BT, WPD, and WWU; 
	In progress

	d) Investigate blockage to arch culvert at Home Farm Court; 
	In progress

	e) Survey watercourse, manhole and pipe branch entering MH5504 from Church House Inn;
	DCC to schedule

	f) CCTV camera and level survey of the pipe system between Hilary Cottage and The Firs; 
	Completed + DCC Highways now clearing blockages found.

	g) Topographical survey of land adjacent to and south of Deane House identified for flood storage and cut off ditches; 
	Completed

	h) Topographical survey of Deane Road if additional gullies are to be constructed;
	n/a at this stage

	i) BRE 365 Infiltration tests at Teignharvey Lane if infiltration is to be considered;
	n/a at this stage

	j) CCTV survey of gullies and pipes in Ivy Tree Hill  Stoke Cross to determine capacity;
	DCC to schedule

	k) Open MH5521 or MH5524 to confirm depths and connectivity (Outside Victoria Farm); 
	DCC to schedule

	l) Topographical survey of land between Village Hall and Pools Weir Road identified for flood storage.  This should include SWW MH cover levels, invert levels and pipe branches even if chambers are buried; 
	
Completed

	m) Topographical survey of land between Hilary Cottage and The Mead if insufficient volume is available between the Village Hall and Pools Weir Road.
	DCC to schedule




See below: Updated Stokeinteignhead Action Plan 2015/2016 


Jessica Bott
Senior Flood Risk Officer
Devon County Council Flood Risk Managemet


Stokeinteignhead Action Plan 2015/2016
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Action
	2015
	2016

	
	Feb
	Mar
	Apr
	May
	Jun
	Jul
	Aug
	Sep
	Oct
	Nov
	Dec
	Jan
	Feb
	Mar
	Apr 
	May 
	Jun 
	Jul 
	Aug 
	Sep 

	Silt trap:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Survey and design
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Procure and construct
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Maintenance schedule to be agreed by Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Highway agreement/ownership notice etc.
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Obtain LiDAR/topographic data for further work
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Engineer meet with Flood Group re: village drainage plan
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Community Pathfinder Project liaise with Parish
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Hydraulic modelling
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Optioneering
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Costing
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Production of Project Appraisal Report (PAR)
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Environmental report/statement:
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	  - Environmental Survey
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	  - Outline further investigations necessary
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Outline design for PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Submit PAR
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Detailed design of preferred option
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Final PAR approval
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Serve any relevant notices
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Procurement
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Tender review
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Construction phase
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	

	Parish Council/residents comms and updates
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	 
	
	
	
	
	
	



	 
	Not completed
	
	In progress
	
	Completed 



